## mit Arbeit
JUNE	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
																						CONCEPTION, NAME FINDING, SUPERVISORS?			Arbeit	VACATION			Arbeit	teensy ISR Coding
																						get the teensy running!

JULY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	EXPLORING PERFORMATIVE ELEMENTS – conception, coding, experiments and tests, iterations
	Anmeldung MA	Arbeit	Arbeit	teensy sensor calibration		BRAINSTORMING, RESEARCH AND CODING			Arbeit	Arbeit			Arbeit	Arbeit	EXECUTION AND ITERATION					Arbeit	Arbeit	Arbeit	BRAINSTORMING, RESEARCH AND CODING	Arbeit			EXECUTION AND ITERATION	DEADLINE: clear idea about what to do technically	Arbeit	Arbeit
	teensy ISR coding					QUANTIZATION									RHYTHM DETECTION I / engine								RHYTHM DETECTION II / variations and figures

AUGUST	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	V A C A T I O N																V A C A T I O N							Arbeit

SEPTEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	CODING FUNCTIONS I		Arbeit	Arbeit			CODING FUNCTIONS II			Arbeit	Arbeit			Arbeit	Arbeit	Arbeit	HARDWARE PROTOTYPING				HARDWARE PROTOTYPING		DEADLINE: conception of needed hardware	Arbeit	Arbeit			HARDWARE DESIGN		ORDERING OF HARDWARE			SCORE GENERATION??
	deciding on performative practices						performative practice										performative practice				performative practice

OCTOBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	Arbeit	Arbeit			Arbeit	Arbeit	...waiting for hardware…					Arbeit	Arbeit	...waiting for hardware…					Arbeit	Arbeit	Arbeit	HARDWARE ASSEMBLY				HARDWARE ASSEMBLY & TESTING			Arbeit	Arbeit
					performance setting? narrative, visuals, …							performance setting? narrative, visuals, …

NOVEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	PREPARING THE CONCERT/PERFORMANCE																						LAST WEEK OF MADNESS
		visuals, lights, performance preparation							visuals, lights, performance							orga: lights, setup, drinks			rehearsals				rehearsals		SETUP	final rehearsals				FINAL CONCERT			Arbeit im Novemberaussetzen?
		more hardware testing							setting up hardware														SETUP

## 2020-06-25 mit Arbeit
JUNE	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
																						CONCEPTION, NAME FINDING, SUPERVISORS?			Arbeit	VACATION			Anmeldung MA
																						get the teensy running!							get teensy running!

JULY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	EXPLORING PERFORMATIVE ELEMENTS – conception, coding, experiments and tests, iterations
	Arbeit	Arbeit	Arbeit			BRAINSTORMING, RESEARCH AND CODING			Arbeit	Arbeit			Arbeit	Arbeit	EXECUTION AND ITERATION					Arbeit	Arbeit	Arbeit	BRAINSTORMING, RESEARCH AND CODING	Arbeit			EXECUTION AND ITERATION	DEADLINE: clear idea about what to do technically	Arbeit	Arbeit
						QUANTIZATION									RHYTHM DETECTION I / engine								RHYTHM DETECTION II / variations and figures

AUGUST	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	V A C A T I O N																V A C A T I O N							Arbeit

SEPTEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	CODING FUNCTIONS I		Arbeit	Arbeit			CODING FUNCTIONS II			Arbeit	Arbeit			Arbeit	Arbeit	Arbeit	HARDWARE PROTOTYPING				HARDWARE PROTOTYPING		DEADLINE: conception of needed hardware	Arbeit	Arbeit			HARDWARE DESIGN		ORDERING OF HARDWARE
	deciding on performative practices						performative practice										performative practice				performative practice

OCTOBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	Arbeit	Arbeit			Arbeit	Arbeit	...waiting for hardware…					Arbeit	Arbeit	...waiting for hardware…					Arbeit	Arbeit	Arbeit	HARDWARE ASSEMBLY				HARDWARE ASSEMBLY & TESTING			Arbeit	Arbeit
					performance setting? narrative, visuals, …							performance setting? narrative, visuals, …

NOVEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	PREPARING THE CONCERT/PERFORMANCE																						LAST WEEK OF MADNESS
		visuals, lights, performance preparation							visuals, lights, performance							orga: lights, setup, drinks			rehearsals				rehearsals		SETUP	final rehearsals				FINAL CONCERT			Arbeit im Novemberaussetzen?
		more hardware testing							setting up hardware														SETUP

## ohne Arbeit
JUNE	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
																						CONCEPTION, NAME FINDING, SUPERVISORS?							Anmeldung MA

JULY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	EXPLORING PERFORMATIVE ELEMENTS – conception, coding, experiments and tests, iterations
						BRAINSTORMING, RESEARCH AND CODING							EXECUTION AND ITERATION							BRAINSTORMING, RESEARCH AND CODING							EXECUTION AND ITERATION			DEADLINE: clear idea about what to do technically

AUGUST	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	V A C A T I O N																V A C A T I O N							CONCEPTION, PRECISE TECHNICAL RESEARCH, FINAL IDEAS
																								deciding on performative practices

SEPTEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	HARDWARE PROTOTYPING						HARDWARE PROTOTYPING							HARDWARE PROTOTYPING				DEADLINE: conception of needed hardware			HARDWARE DESIGN							HARDWARE DESIGN
	performative practice						performative practice							performative practice

OCTOBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
		ORDERING OF HARDWARE			...waiting for hardware…							...waiting for hardware…							HARDWARE ASSEMBLY							HARDWARE ASSEMBLY & TESTING
					performance setting? narrative, visuals, …							performance setting? narrative, visuals, …

NOVEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	PREPARING THE CONCERT/PERFORMANCE																						LAST WEEK OF MADNESS
		visuals, lights, performance preparation							visuals, lights, performance							orga: lights, setup, drinks			rehearsals				rehearsals		SETUP	final rehearsals				FINAL CONCERT
		more hardware testing							setting up hardware														SETUP