## ohne Arbeit
JUNE	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
																						CONCEPTION, NAME FINDING, SUPERVISORS?							Anmeldung MA

JULY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	EXPLORING PERFORMATIVE ELEMENTS – conception, coding, experiments and tests, iterations
						BRAINSTORMING, RESEARCH AND CODING							EXECUTION AND ITERATION							BRAINSTORMING, RESEARCH AND CODING							EXECUTION AND ITERATION			DEADLINE: clear idea about what to do technically

AUGUST	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	V A C A T I O N																V A C A T I O N							CONCEPTION, PRECISE TECHNICAL RESEARCH, FINAL IDEAS
																								deciding on performative practices

SEPTEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	HARDWARE PROTOTYPING						HARDWARE PROTOTYPING							HARDWARE PROTOTYPING				DEADLINE: conception of needed hardware			HARDWARE DESIGN							HARDWARE DESIGN
	performative practice						performative practice							performative practice

OCTOBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
		ORDERING OF HARDWARE			...waiting for hardware…							...waiting for hardware…							HARDWARE ASSEMBLY							HARDWARE ASSEMBLY & TESTING
					performance setting? narrative, visuals, …							performance setting? narrative, visuals, …

NOVEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	PREPARING THE CONCERT/PERFORMANCE																						LAST WEEK OF MADNESS
		visuals, lights, performance preparation							visuals, lights, performance							orga: lights, setup, drinks			rehearsals				rehearsals		SETUP	final rehearsals				FINAL CONCERT
		more hardware testing							setting up hardware														SETUP

## mit Arbeit
JUNE	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
																						CONCEPTION, NAME FINDING, SUPERVISORS?			Arbeit	Arbeit			Anmeldung MA

JULY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	EXPLORING PERFORMATIVE ELEMENTS – conception, coding, experiments and tests, iterations
	Arbeit	Arbeit	Arbeit			BRAINSTORMING, RESEARCH AND CODING			Arbeit	Arbeit			Arbeit	Arbeit	EXECUTION AND ITERATION					Arbeit	Arbeit	Arbeit	BRAINSTORMING, RESEARCH AND CODING	Arbeit			EXECUTION AND ITERATION	DEADLINE: clear idea about what to do technically	Arbeit	Arbeit

AUGUST	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	V A C A T I O N																V A C A T I O N							Arbeit

SEPTEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	CONCEPTION, PRECISE TECHNICAL RESEARCH, FINAL IDEAS		Arbeit	Arbeit			HARDWARE PROTOTYPING			Arbeit	Arbeit			Arbeit	Arbeit	Arbeit	HARDWARE PROTOTYPING				HARDWARE PROTOTYPING		DEADLINE: conception of needed hardware	Arbeit	Arbeit			HARDWARE DESIGN		ORDERING OF HARDWARE
	deciding on performative practices						performative practice										performative practice				performative practice

OCTOBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	Arbeit	Arbeit			Arbeit	Arbeit	...waiting for hardware…					Arbeit	Arbeit	...waiting for hardware…					Arbeit	Arbeit	Arbeit	HARDWARE ASSEMBLY				HARDWARE ASSEMBLY & TESTING			Arbeit	Arbeit
					performance setting? narrative, visuals, …							performance setting? narrative, visuals, …

NOVEMBER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
	PREPARING THE CONCERT/PERFORMANCE																						LAST WEEK OF MADNESS
		visuals, lights, performance preparation							visuals, lights, performance							orga: lights, setup, drinks			rehearsals				rehearsals		SETUP	final rehearsals				FINAL CONCERT			Arbeit im Novemberaussetzen?
		more hardware testing							setting up hardware														SETUP